## Deployment Checklist
Phase | Check | Priority | What goes wrong if you skip it | Done?
Pre-flight | Know exactly what is in the deployment (a readable component list) | Critical | You cannot assess risk on "the Q3 changes"
Pre-flight | Know the blast radius of each change — every reference to it | Critical | The reference you miss is the one that breaks production
Pre-flight | Diff sandbox against production (catch drift / prod-only hotfixes) | High | You overwrite a change that only exists in prod
Pre-flight | Run a validation-only ("check only") deploy with the tests that will run | Critical | Failures surface mid-deploy instead of on your schedule
Pre-flight | Confirm at least 75% org-wide Apex coverage and all tests pass | Critical | A production deploy involving Apex rejects without it
Pre-flight | Capture the current production state of everything you are changing | High | No captured before-state means no rollback
Deploy | Order components by dependency (field before the flow that uses it) | High | Deploy fails or references dangle
Deploy | Handle deletions separately — change sets add/update, they do not delete | Medium | Removed components linger; the cleanup never happens
Deploy | Deactivate flows/components before deleting them | Medium | Deletion is blocked by active or referenced state
Deploy | Choose the test level intentionally (local vs all tests) | Medium | Surprise runtime or missed failures
Deploy | Quick-deploy the validated result within the window Salesforce keeps it | Low | Re-running validation wastes time
Validate | Spot-check real behavior with a real record | Critical | "Succeeded" is not the same as "works"
Validate | Confirm the automation actually fires as intended | High | Silent automation break
Validate | Run the report or dashboard that matters | High | Empty or wrong numbers in production
Validate | Check integrations touching changed fields still round-trip | High | External systems start rejecting records
Rollback | Have the previous state staged as a deploy — there is NO native rollback | Critical | "Undo" becomes reconstruct-under-pressure
Rollback | Written revert steps and who makes the call | High | "We will just roll it back" is not a plan
Rollback | Flag anything irreversible (deleted data, a type change that dropped values) | Critical | Those do not roll back at all

## Scorecard
Deployment readiness
Total checks
Completed (Yes)
Not applicable
Critical still outstanding
Verdict